## Slide 1: FIELDS early project results
Francesca Sanna, Project Manager
francesca.sanna@unito.it
2nd Partnering meeting
29 June 2020
UNITO

## Slide 2: Agenda - Project results & Future activities
 | AGENDA | Contributors
13:50 | Welcome | Remigio Berruto (UNITO)
14:00 | WP1 - Skills needs identification (ISEKI) Task 1.1: State of the Art (UNITO), M1-M6 Task 1.2: Stakeholders strategic mapping (LLL-P), M1- M6 Task 1.3: Country and EU focus groups (ISEKI), M2-M9 Task 1.4: Bottom-up surveys (ICOS), M9-M12 Task 1.5: Future trends analysis (WUR), M8-M15 | Francesca Sanna (UNITO) Riccardo Gulletta (LLL-P) Luis Mayor (ISEKI) Billy Goodburn (ICOS) Jacques Trienekens (WUR)
14:40 | WP1 – Q/A | 
14:50 | WP3 - New tools and training design (UNITO) Task 3.1: Methodology definition (UNITO), M4-M9 | Berruto (UNITO)
15:05 | WP3 – Q/A | 
15:10 | WP4 - Implementation (AERES) Task 4.3: Map creation, update and use (UNITO), M4-M48 Task 4.4: Translation (CONFAGRI), M4-M48 | Francesca Sanna (UNITO) Camilla Tomao (CONFAGRI)
15:20 | WP4 – Q/A | 
15:30 | Virtual Coffee break | 

## Slide 3: Agenda - Project results & Future activities
 | AGENDA | Contributors
15:45 | WP5 - Sustainable action plan (ICOS) Task 5.1: National and EU regulatory frameworks (ConfagriPT), M7-M20 Task 5.2: Funding opportunities (LLL-P), M7-M20 | Claúdia Camacho (ConfagriPT) Riccardo Gulletta (LLL-P)
15:55 | WP5 – Q/A | 
16:00 | WP6 – Quality Assessment (CERTH) D6.1: Quality plan (CERTH), M1-M4 D6.2: Evaluation Grids (INFOR), M5-M6 | Aivazidou/Rodias (CERTH) Giuseppe Vanella (INFOR)
16:20 | WP6 – Q/A | 
16:30 | WP7 - Dissemination and communication (ACTIA) Task 7.1: Dissemination plan (LVA), M1-M9 Task 7.2: Communication and dissemination campaign (FIAB), M1-M48 | Cotillon/Cornuau (ACTIA) Drausinger/Stollewerk (LVA) Concha Avila (FIAB)
16:50 | WP7 – Q/A | 
17:00 | WP8 - Project Management (UNITO) Task 8.1: Decision making and internal communication, M1-M4 Task 8.2: Administrative and financial management, M1-M48 | Remigio Berruto / Francesca Sanna (UNITO)
17:20 | Future activities and next meetings | 
17:50 | Questions and Comments | 
18:00 | Conclusion and greetings | 

## Slide 4: WP1 – Skills needs identification (ISEKI)
To collect the information about the state of the art, UNITO created online databases storing all relevant research. The database was created in the FIELDS project management platform and it will be available through the project’s public website.
Task 1.1 State of the Art (UNITO), M1 – M6
Deliverable 1.1 Stakeholders strategic plans and analysis report (UNITO), M1 – M6
The growth strategy of the sector will be summarized through the available material and directives from the EU, producers associations and industries, in a comprehensive report in M6 by UNITO, UHOH, CONFAGRI and WUR
Meeting held the 25 June to define the firsts steps on the growth strategy of the sector
15 contribution already received from the partners

## Slide 5
Database feature: avoid duplication, system does not save the same records previously inserted
More info in the guidelines available in the management portal
http://www.erasmus-fields.eu/management/?q=node/1191
Deliverable 1.2 Repository of previous projects, results and best practices (UNITO), M1 – M6
  Type of Deliverable: Technological/Service outputs: refer to virtual platform/services developed and provided to target beneficiaries in the context of the Fields project. It will be validated based on the document drafted to describe the features of the technological output.
D1.2 in preparation, finalizing the revised draft.
A target of 30 institutes to populate the platform is set for year one and a target of minimum 120 is set until the end of the project.

## Slide 6: Organisations/stakeholder database
146 Organisations inserted so far!
http://www.erasmus-fields.eu/management/?q=organisation

## Slide 7: Curricula/Courses database
http://www.erasmus-fields.eu/management/?q=curricula-courses-database
93 Curricula/Courses inserted so far!
21 Bio-economy; 57 Sustainability; 11 Digitalization; 15 Soft-skill;
10 Entrepreneurship; 43 Business as usual

## Slide 8: Best practices database
http://www.erasmus-fields.eu/management/?q=best-practices-database
3 Best practices inserted so far!

## Slide 9: Projects database
http://www.erasmus-fields.eu/management/?q=projects-database
19 Project inserted so far!
4 Bio-economy; 13 Sustainability; 7 Digitalization; 2 Soft-skill;
4 Entrepreneurship; 3 Business as usual

## Slide 10: Policy and advocacy
http://www.erasmus-fields.eu/management/?q=policy-and-advocacy
18 Policy and advocacy inserted so far!

## Slide 11
Questions and comments
At the end of the WP session

## Slide 12: WP4 – Implementation (AERES)
Task 4.3: Map creation, update and use (UNITO), M4-M48
Francesca Sanna (UNITO)
D4.3: Online public platform and map (M12)
Task 4.4: Translation (CONFAGRI), M4-M48
Camilla Tomao (CONFAGRICOLTURA)

## Slide 13: Task 4.3: Map creation, update and use
It will be kept updated during the project lifetime and maintained afterwards. The databases will be further used in Task 4.3 and integrated with a geographical map as an additional layer on the website.
About 65 records inserted so far!

## Slide 14: Task 5.2: Funding opportunities (LLL-P), M7-M24
In this task partners will study and list the funding opportunities available to support the skills strategies and the future use of FIELDS’ outputs.
Two levels will be studied (regional/national and EU levels), each partner will list the regional and national funding opportunities using the EU tender portal and the local authorities materials.
The following partners will be responsible for each country:
Austria: LVA and AP
France: ACTIA, AC3A
Germany: UHOH
Greece: GAIA, SEVT, and CERTH
Ireland: ICOS
Italy: CONFAGRI and INFOR
Netherlands: WUR and AERES
Portugal: Confagri PT
Spain: FIAB, SCOOP
Slovenia: GZS-ZKZP
All opportunities will be uploaded in the platform made in T4.3 to ensure easy monitoring and use by partners and external stakeholders.

## Slide 15: WP6 – Quality Assessment (CERTH)
Task 6.1 – Quality Plan (CERTH)
D6.1: Quality plan (CERTH), M1-M4
Aivazidou/Rodias (CERTH)
D6.2: Evaluation Grids (INFOR), M5-M6
Giuseppe Vanella (INFOR)
FOR THE HIGH STEERING COMMITTEE (HSC):
  D6.2 Annex I - Deliverable assessment Grid
  Downloadable from the management portal
http://www.erasmus-fields.eu/management/?q=node/1164

## Slide 16: WP7 - Dissemination and communication (ACTIA)
Task 7.1: Dissemination plan (LVA), M1-M9
Julian Drausinger, Katharina Stollewerk (LVA)
D7.1 Dissemination plan (M9)
Task 7.2: Communication and dissemination campaign (FIAB), M1-M48
Concha Avila (FIAB)
D7.2: Public Website (M3)
D7.3: Project leaflet and poster (M6)
D7.4: Report on dissemination action (M48)
Christophe Cotillon, Gemma Cornuau (ACTIA)

## Slide 17: T7.2 Communication and dissemination campaign (FIAB)
https://lucarivastudio.ecommerceopen.it/erasmusfields/
First layout, also optimized for mobile phone
Link to be added in the organisation website
D7.2: Public Website (M3)
D7.3: Project leaflet and poster (M6)
www.erasmus-fields.eu
Fist draft ready, prepared by an esternal desiger. It will be available in the project’s partner languages in hard copy, as well as in electronic format through the project website.
Feedback and comments are very welcome!

## Slide 18: Templates

## Slide 19: WP8 - Project Management (UNITO)

## Slide 20: WP8 - Project Management (UNITO)
19 signed pages received so far
D8.1: Consortium Agreement (M1)
Task 8.1: Decision making and internal communication (UNITO), M1-M48

## Slide 21: WP8 - Project Management (UNITO)
Task 8.2: Administrative and financial management, M1-M48
Propose: Webinar on financial issues, use of timesheet template, deadlines etc. – Q/A
Organised in October/November (fist reporting in M13)

## Slide 22: Next meetings
Face-to-face meeting in Ljubljana in September/October?
Meeting | Date | Place | Host
Kick-off | M1 | Turin, Italy | UNITO
Management Meeting 1 (MM1) | M13 | Vienna, Austria | ISEKI/LVA
MM2 | M25 | Paris | ANIA
MM3 | M37 | Wageningen, Netherlands | WUR
MM4 | M45 | FIAB | Spain
Final conference in Brussels | M48 | FDE | Brussels
In addition, the HSC will meet also on M6, M18, M31 and M42, with only representatives of the WP leaders. Other partners are welcome to participate.
In addition, a virtual conference call will be organised every 2 months to closely monitor the evolution of tasks and deliverables of the project
The HAB with representatives of COPA COGECA will participate to meetings in M13 and M45 upon invitation

## Slide 23: Thank you for your attention!
Francesca Sanna, FIELDS project manager
francesca.sanna@unito.it